SEGUESYNC

Client Document

Project Proposal & Statement of Work

Meeting & Board Management Platform — Build Engagement

|  | Prepared for: Project Stakeholders Prepared by: SegueIT — Product & Engineering Date: August 2026 |  |
| --- | --- | --- |

# Table of Contents

(Right-click and choose "Update Field" in Word if this list appears empty on first open.)

Table of Contents	2

1. Introduction	3

2. Project Overview	3

3. Scope of Work	3

3.1 Out of Scope	3

3.2 Deliverables	3

4. Project Timeline	4

5. Payment Milestones	4

6. Acceptance Criteria	4

7. Assumptions & Dependencies	4

8. Change Requests	5

9. Agreement	5

# 1. Introduction

This Statement of Work (SOW) describes the project to design and build SegueSync, a meeting and board management platform, on behalf of the client. It sets out what will be delivered, in what order, over what timeframe, and the commercial terms under which the work is carried out.

This document should be read alongside the Requirements Document (BRD), which describes the detailed business requirements this project satisfies.

# 2. Project Overview

SegueSync gives an organisation's board or committee a single system to schedule meetings, build agendas, generate meeting packs automatically, capture minutes, track decisions and follow-up actions, and hold votes between meetings. It replaces manual, email- and spreadsheet-based meeting administration with one connected, auditable platform.

| Schedule a Meeting | ➜ | Build the Agenda | ➜ | Auto-Generate Board Pack | ➜ | Hold the Meeting | ➜ | Capture Minutes | ➜ | Track Actions & Decisions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Figure 1 — the core cycle every meeting goes through inside SegueSync.

# 3. Scope of Work

The project is delivered in five phases. Each phase is a working, demoable increment, not a throwaway prototype — the client can review and provide feedback at the end of every phase before the next one begins.

| Phase | What It Delivers |
| --- | --- |
| Phase 1 — MVP | A board can fully run one real meeting: schedule it, build & publish the agenda, generate the Board Pack, take minutes, and track the resulting actions. Includes account signup and secure login. |
| Phase 2 — Governance Records | Decisions register, document repository, conflicts-of-interest register, member profiles, full audit trail, personal dashboard. |
| Phase 3 — Async Governance | Electronic voting between meetings (Flying Minutes), circulated reports, configurable quorum/voting rules, sub-committees, annual work plan. |
| Phase 4 — AI Layer | AI-drafted agendas, AI-drafted minutes from an uploaded transcript, and an AI assistant that answers questions over the board's own records with cited sources. |
| Phase 5 — Enterprise & Compliance | Multi-factor authentication, electronic signatures, fine-grained access roles, security policy controls, and billing infrastructure if the platform is commercialised. |

## 3.1 Out of Scope

- Native mobile apps (the web app works on mobile browsers, but no dedicated iOS/Android app is built).

- Migrating historical minutes/records from any previous system — the platform is assumed to start fresh.

- Custom per-region legal/compliance certification beyond what is noted for Phase 5.

## 3.2 Deliverables

- A working, deployed application at the end of each phase, accessible for client review.

- Access to the source code repository, with setup documentation.

- A short progress demonstration (screenshots or a recorded walkthrough) at the end of each phase.

- A user guide for board administrators and members, delivered near project completion.

# 4. Project Timeline

Indicative roadmap across a 6-month build, assuming a small team of 2–3 engineers. Phases are shown with a short handoff overlap, since design work on the next phase typically starts before the previous one is fully wrapped.

| Phase | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 — MVP |  |  |  |  |  |  |
| Phase 2 — Records |  |  |  |  |  |  |
| Phase 3 — Async Gov. |  |  |  |  |  |  |
| Phase 4 — AI Layer |  |  |  |  |  |  |
| Phase 5 — Enterprise |  |  |  |  |  |  |

Figure 2 — indicative 6-month roadmap. Phases 1–2 alone (~2–2.5 months) already deliver a genuinely usable product, should the client wish to review progress and re-scope later phases at that point.

# 5. Payment Milestones

Suggested phase-linked payment structure — final percentages and amounts to be agreed and inserted before signing.

| Milestone | Trigger | Suggested Payment |
| --- | --- | --- |
| Project Kick-off | Signing of this SOW | 20% |
| Phase 1 Complete | MVP demoed and accepted by client | 20% |
| Phase 2 Complete | Governance record-keeping features accepted | 20% |
| Phase 3 Complete | Async governance features accepted | 15% |
| Phase 4 Complete | AI layer accepted | 15% |
| Phase 5 Complete / Final Handover | Enterprise & compliance features accepted, project closed | 10% |

# 6. Acceptance Criteria

A phase is considered complete and accepted when:

- All features listed for that phase are demonstrated working in a deployed environment.

- The client has been given no fewer than 5 business days to review and raise issues.

- Any issues raised are either resolved or explicitly deferred to a later phase by written agreement.

# 7. Assumptions & Dependencies

- The client will provide branding assets (logo, colour palette) before Phase 2 begins.

- Email delivery depends on a third-party transactional email service (e.g. Resend/SendGrid) being configured, with any associated cost borne by the client unless otherwise agreed.

- AI features (Phase 4) depend on an external AI provider's API being reachable and within its usage limits.

- Timely feedback from the client at the end of each phase is required to keep the timeline in §4 on track.

# 8. Change Requests

Any request to add or materially change scope after this SOW is signed will be documented as a separate Change Request, with its own effect on timeline and cost agreed in writing before work begins on it.

# 9. Agreement

By signing below, both parties agree to the scope, timeline, and payment terms described in this Statement of Work.

| For the Client Signature Name, Title & Date | For SegueIT (Vendor) Signature Name, Title & Date |
| --- | --- |